## Standard
| Project Implementation Process (PIP) Stage | PIP Reference | Funder (Lead Agency) | End user | Purchaser (DPTI) | Provider (design/construction team) | Project Director | Manager Medium Works Program | Cost Manager | Contractor | Subcontractor | Project Director (Lead Agency Representative) | Manager Medium Works Program (DPTI Representative) | Contractor (Architect) | Subcontractor | Cost Manager (role in addition to Contractor services)
GOVERNMENT STRATEGIES AND KEY DIRECTIONS |  |  | R | [8 empty] | DPTI = Department of Planning, Transport and Infrastructure, PCG = Project Control Group
IDEAS TO MEET NEEDS |  |  | R | I | I | [6 empty] | R = Responsibility, I = Input
CORPORATE PLANNING PHASE |  |  | R | I | I
| Determine broad Lead Agency parameters for project program, budget and quality |  | R | I | I |  | R |  |  |  |  | Manage that there is approval by the Lead Agency delegate of the initial scope and associated budget, program and quality standards | Assist the Lead Agency to determine initial parameters by providing DPTI building industry data, knowledge and lessons learned.
CONCEPT PHASE |  | 5.1
| Project Control Group |  | I | I | R | I | I | I | I | R | I | Attend and report to milestone Project Control Group meetings | Attend and report to milestone Project Control Group meetings | Chair, minute and report to regular Project Control Group meetings | Attend and report to regular Project Control Group meetings
| Design Team |  | I | I | I | R | I | I | I | R | I | Attend milestone design team meetings as required. | Attend milestone design team meetings as required. | Chair and minute regular design team meetings. | Attend regular design team meetings.
| Monthly Reporting Regime |  |  |  | R | I | I | R | R | R | I |  |  | Prepare and submit on a monthly basis a report incorporating comments from disciplines providing status of all work and nominating all issues of concern and the management being applied to them. Consult with DPTI MMWP. | Input on a monthly basis to report prepared by the Contractor providing status of all work and nominating all issues of concern and the management being applied to them. | Prepare and submit on a monthly basis a report providing status of budget, commitment and analysis of trends in contingency expenditure nominating all issues of concern and the management being applied to them. Consult with DPTI Budget Adviser.
DESIGN SERVICES | Establish project control group and other organisation structures |  | I | I | R | [6 empty] | Determine who will represent Lead Agency interests on the Project Control Group | Assist the Lead Agency to establish the project organisation structure by providing organisation models. Establish Project Control Group
| Appoint project team to develop the concept |  | I |  | R |  | I | R |  |  |  | Propose required resources and whether internal or private sector | Participate in agreement on required resources and whether internal or private sector
| Prepare professional service contractor tenders |  | I | I | R |  | I | R |  |  |  | Provide detailed project and services brief to facilitate the establishment of an appropriate project team from internal and external resources | Identify tender fields, using the DPTI Prequalification register and initial risk analysis. Prepares brief, conditions of tender and conditions of contract. | Submit services and fees adequate and appropriate for the full consultancy services in accordance with the professional service contractor tender documents. Where relevant assist in the tender and award of other professional service contractor contracts | Submit services and fees adequate and appropriate for the full consultancy services in accordance with the professional service contractor tender documents. | Submit services and fees adequate and appropriate for the full consultancy services in accordance with the professional service contractor tender documents. Where relevant assist in the tender and award of other professional service contractor contracts
| Tender assessment |  | I | I | R |  | I | R |  |  |  | Input into the selection of required professional service contractors | Manage the assessment of tenders and prepares recommendations to the Lead Agency and DPTI delegates for expenditure and contract approval.
| Appoint the Design Team | [11 empty] | On approval from the Lead Agency and DPTI delegates, manages that Contracts Management administers tender acceptance of Contractor contract.
| Project Team management and coordination |  |  |  | I | R | I | I | I | I | I |  | Manage that there is implementation of effective team coordination | Implement agreements on design team coordination. Implement effective team briefings and coordination | Implement agreements on design team coordination
| Establish team briefing, communication and reporting |  |  |  | R | I | I | I | I | I | I | Provide detailed DPTI and professional service contractor briefings | Manage that there is implementation of briefing, and communication and reporting systems in accordance with DPTI policies | Implement effective briefing, communication and reporting systems in accordance with DPTI policies. Manage design team briefings and implement agreements on team communication and reporting. | Attend design team briefings and implement agreements on team communication and reporting
| Develop project concept to meet service delivery needs |  | I | I | I | R | I | I | I | R | I | Overview concept preparation | Overview briefing of and concept development by the design team to ensure input of relevant DPTI standards, guide notes and lessons learned. | Design concept options | Design concept options liaising with Contractor and other disciplines | Cost concept options
| Confirm service directions |  | R | I |  |  | R |  |  | I |  | Manage that the service directions are resolved through the SC and other appropriate bodies to clearly define the service needs and objectives. |  | Challenge service directions to clarify briefed requirements
| Site investigations |  | I | I | I | R | I | I | I | R | I | Provide any background information on the site held by the Lead Agency and End Users. | Facilitate the site investigation process by ensuring input of DPTI information on site and assets. | Investigate and report on site and ownership details, carry out assessment of impact on any aboriginal land or sacred site, any listed or proposed heritage site or building, any significant trees. | Input into site investigations. | Consider and incorporate costs relating to site investigations.
| Analyse needs and market research in detail |  | R | I | I | I | R |  |  | I |  | Manage that all appropriate trends to be taken into account in the definition of service needs are identified and endorsed by the SC. | Contribute to the definition of service needs in regard to building asset data base information, costing models, cash flow and program solutions.
| Clarify the functional objectives of the project. |  | R | I | I | I | R | I | I | I | I | Manage that the project objectives are sufficiently clear and properly endorsed by the SC to form the basis of the design team's work. | Manage that the project objectives are clearly stated in the project and professional service contractors briefs. | Incorporate into the concept options the project functional and other objectives. | Incorporate into the concept options the project functional objectives. | Incorporate into the cost plan any costs arising out of project functional objectives.
| Identify statutory, planning and environmental issues |  |  |  | I | R | I | I | I | R | I | Input as relevant into the achievement of statutory, planning and environmental approvals | Input as relevant into the achievement of statutory, planning and environmental approvals | Provide advice from all relevant parties, agree timing and scope of approvals with DPTI and achieve statutory, planning and environmental approvals. | Provide advice and assist in the achievement of approvals. | Incorporate into the cost plan any cost issues arising out of statutory, planning or environmental approvals
| Identify cultural and heritage issues |  | R | I | I | I | R | I | I | R | I | Ensure that the brief of requirements identifies any known cultural or heritage issues. | Contribute to the definition of heritage issues through the use of DPTI historic buildings asset information. | Provide advice from all relevant parties, agree timing and scope of any approvals with DPTI and achieve relevant heritage or cultural approvals. | Provide advice and assist in the achievement of approvals. | Incorporate into the cost plan any costs arising out of cultural or heritage issues.
| Define key operational parameters and functional relationships |  | R | I | I | I | R | I |  | I | I | Manage that the key operational and functional relationships are sufficiently clear and properly endorsed by the End Users, PCG and the SC to form the basis of the design team's work. | Manage that parameters and relationships are formally defined by the Lead Agency and responded to by the Contractor and disciplines. | Coordinate the work of the design team to meet the defined project parameters. Design to the defined parameters and functional relationships and manage that they are the basis for the disciplines' work. Advise of any outstanding information immediately it is evident. | Design to the defined parameters and functional relationships. Advise of any outstanding information immediately it is evident. | Prepare a cost plan to the defined parameters. Advise of any outstanding information immediately it is evident.
| Define project parameters, quality standards, and budget estimate |  | R | I | I | I | R | I | I | I | I | After consultation within the Lead Agency and the End Users, provide a brief of the required project scope, quality standards, project program and budget. | Manage that there is a brief from the Lead Agency and the End Users of the required project scope, quality standards, project program and budget. | Coordinate the preparation of the brief and respond with a design to meet draft schedule of areas. | Input into draft brief and draft schedule of areas. | Prepare indicative benchmark costings and order of cost estimates based upon the brief and the design prepared by the Contractor.
| Prepare order of cost estimate |  | I | I | I | R | I | I | R | I | I | Make available detailed brief and any background information to inform on project cost | Manage that DPTI information on existing buildings and on rates/market etc is researched and reviewed and is incorporated into the order of cost estimate prepared. | Coordinate the preparation of the order of cost estimate by providing design detail sufficient to prepare an order of cost estimate. | Input into the order of cost estimate. | Prepare order of cost estimate to complete project based on brief and historical data
| Identify Government, DPTI and Lead Agency policies and codes relevant to the project. Refer to the Project Implementation Process and the Government Buildings Energy Strategy |  | R |  | R |  | R | R | I | I | I | Make available all relevant policies and codes to the project team. | Manage that information on policies and codes is available to the project team for review. | Review requirements of policies and codes to manage that the requirements are understood, incorporated into the design proposals and documented. | Review requirements of policies and codes to manage that the requirements are understood, incorporated into the design proposals and documented. | Review requirements of policies and codes to understand and incorporate the potential cost impact.
| Undertake Risk Analysis |  | I | I | R | I | I | R | I | I | I | Manage that the PCG reviews the professional service contractors/DPTI risk analysis and advises the SC. | Work with the Contractor to provide a comprehensive appraisal of project risks. | Prepare Risk Management report on risk profile. | Work with DPTI to provide a comprehensive appraisal of project risks
| Contingencies |  | I | I | R | I | I | R | I | I | I |  | Contribute to assessment of required design and construction contingency allowances. | Manage that there is assessment and determination on the appropraite design and constrcution contingency allowances on the basis of risk analysis. | Contribute to assessment of required design and construction contingency allowances.
| Identify existing building issues |  | I | I | I | R | I | I | I | R | I | Make available all appropriate information and assist in site survey processes. Organise End User staff input as appropriate to facilitate clear understanding by the professional service contractors. | Manage that DPTI information on existing buildings is researched, reviewed and forms part of design team proposals. | Review existing audit reports and surveys of site buildings and environs to manage that the physical condition and status of code compliance is understood, documented and taken into consideration in proposals. | Review existing audit reports and surveys of site buildings and environs to manage that the physical condition and status of code compliance is understood, documented and taken into consideration in proposals. | Review information on existing buildings to understand and incorporate the potential cost impact.
| Prepare indicative program |  | I |  | I | R | I | I | I | I |  | Input into indicative program by identifying critical milestones or required staging | Manage that there is assessment and determination on appropriate timeframes for key activities. | Prepare indicative program including milestones, staging and time contingency allowances. | Contribute to preparation of indicative program.
| Identify air-conditioning options and life cycle cost models as required by the Government Buildings Energy Strategy |  | I | I | I | R |  |  | I | I | R |  | Manage that the requirements of ESD policy are implemented | Meet the detailed requirements of the Government Buildings Energy Strategy | Meet the detailed requirements of the Government Buildings Energy Strategy | Cost the detailed requirements of the Government Buildings Energy Strategy into cost plans and estimates
| Consider ESD issues in the brief and design |  | R | I | I | R | R | I | I | R | I | Determine the response to Government ESD policy that will apply to the project | Manage that the requirements of the Government Buildings Energy Strategy are implemented | Coordinate that the ESD policy and brief requirements are met by the design team. | Meet the detailed requirements of the briefed ESD initiatives | Cost the detailed requirements of ESD policy and brief requirements into cost plans and estimates
| Identify procurement options | [12 empty] | Agree with DPTI the procurement options.
| Agree on scope of the concept brief |  | R | I | R | I | I | R | I | I |  | Identify key service delivery issues which should be reviewed in the Concept phase. | Identify key service delivery issues which should be reviewed in the Concept phase. | Evaluate the Concept options against key issues. | Evaluate the Concept options against key issues.
| Prepare estimate of cost | [11 empty] | Manage that there is DPTI input into the estimate through budget risk advice. | Coordinate the work of the design team to prepare the estimate. | Input into the concept cost estimate | Prepare concept cost estimate
| Evaluate concept options (value management) |  | I | I | R | I | I | R | I | I | I | Provide input into strategic value management process | Implement a strategic value management exercise with facilitator if required. | Lead a strategic value management process as required | Provide input into strategic value management process
| Select the preferred Concept option |  | R | I | I | I | R | I | I | I | I | Manage the option selection process to identify the preferred option. | Manage that there is endorsement of the preferred concept option by the PCG and a written confirmation from the Lead Agency. | Manage the process of consultation with the Lead Agency, End Users and PCG to achieve written confirmation of the preferred concept option. | Contribute as required to the selection of the preferred concept option
| Describe the preferred option in a final concept plan and report. |  | I | I | I | R | I | I | I | R | I | Submit final concept brief and design solution report to agency Delegate. | Manage that there is preparation by the design team of the final concept brief and report. | Coordinate the preparation by the design team of the final concept brief and design solution Contract Material. | Contribute to the preparation of the final concept brief and design solution report | Cost the final concept brief and design solution
| DELIVERABLES | 5.1 | [6 empty] | R | R | R |  |  | Three copies of Contract Material and supporting information | Three copies of Contract Material and supporting information | Three copies of Contract Material and supporting information
DESIGN PHASE |  | 5.2
DESIGN SERVICES | Design |  | I | I | I | R | I | I | I | R | I | Coordinate the input of Lead Agency and End User representatives into the design process. Achieve the endorsement of the SC to the design. | Facilitate the design process by ensuring input of DPTI relevant standards, guide notes, lessons learned and clarifying any project management issues. | Develop the design incorporating preferred concept options. Achieve endorsement of the design by the Lead Agency and its End Users. | Contribute to the design incorporating preferred concept options. | Prepare and document cost estimates of the design.
| Briefed Areas Check |  | R | I | I | I | R | I | I | I | I | Manage that the design meets the functional brief and notify of any discrepancies. | Assist with management of the design to brief. | Design within the briefed areas and notify where the design does not meet the brief suggesting options for resolution. | Design within the briefed areas and notify where the design does not meet the brief suggesting options for resolution. | Review the design relative to briefed areas and notify of discrepancies.
| Materials, Climate, Environmental, Energy Use Issues |  | I | I | I | R | I | I | I | R | I | Advise on any aspects of best practice in operation that will effect materials selection or environmental requirements. | Input into issues. | Provide information on proposed materials and identify climatic and environmental issues both immediate and long term. | Provide information on proposed materials and identify climatic and environmental issues both immediate and long term. | Advise on aspects of material selection that have cost advantage/ disadvantage.
| Confirmation of scope of work in addressing existing building issues |  | R | I | I | I | R | I | I | I | I | Confirm the extent of scope in the project in regard to existing building issues. | Manage that the team is provided with any updated project brief confirmed by the Lead Agency | Manage that the design team addresses all issues of scope in regard to addressing existing building issues. Review from previous surveys and documents building condition, maintenance and serviceability problems which may affect viability of the project. Incorporate agreed scope addressing existing buildings into design development. | Review from previous surveys and documents building condition, maintenance and serviceability problems which may affect viability of the project. Confirm interfaces with existing service systems. Incorporate agreed scope addressing existing buildings into design development. | Manage that cost of any scope addressing existing building issues is identified in the cost plan.
| Compliance with DPTI Policy |  |  |  | R | I | I | R | I | I | I | Assist in checking the design against DPTI design policy guidelines. | Review design against specific DPTI design and cost management policy guidelines. | Manage that the design is in compliance with DPTI design policy guidelines. | Design in compliance with DPTI design policy guidelines. | Prepare cost estimates in compliance with DPTI cost management policy guidelines.
| Engineering Solutions |  | I | I | I | R | I | I | I | I | I | Manage that End User Engineering input as appropriate is achieved and that there is Lead Agency support for all Engineering solutions proposed. | Resolve any briefing issues between Lead Agency, End Users and the design team. | Develop with the disciplines a complete, integrated and cost-effective Engineering solution to the brief | Develop the detailed Engineering solution integrated with the Architectural solution and to the cost plan. | Ensure the design is to the cost plan and that all engineering services costs are included.
| Provide Life Cycle Costing |  | I | I | I | R | I | I | R | I | I | Manage that there is Lead Agency and End User input into life cycle costing as appropriate. | Manage that the Government policy requirements in regard to life cycle cost analysis are known and implemented by the design team and Lead Agency. | Manage that all required life cycle cost analysis is provided by the design team. | Analyse Engineering systems and selections for implications in life cycle costing and prepare reports as required. | Prepare life cycle costing analysis and reports as required.
| Review cost plan and undertake value management |  |  |  | I | R | I | I | R | I | I | Input as required in the development of the cost plan. Manage that any Lead Agency costs and FF&E requirements are incorporated in the cost plan. | Input as required in the development of the cost plan. Manage that DPTI cost management policy requirements are integrated into cost management process. | Manage the process of coordination of the design team to provide a cost plan. If costs significantly vary from previously agreed budgets manage that the team develops options to meet the budget and seeks direction on option preference and any changes to scope of work. | Provide all required documents, advice and input to allow the Cost Manager to prepare the cost plan including detailed costing information and estimates on discipline items. Evaluate any issues of concern or alternative proposed by the Cost Manager. | Provide limit of cost plan and cash flows for the total project incorporating all project funds sources. If costs significantly vary from previously agreed budgets, examine through value management ways of changing the brief and design to meet budget guidelines and seek direction on any changes to scope of work.
| Develop detailed project program |  | I | I | I | R | I | R | I | I | I | Define any operational time parameters and input into the development of the timeline after End User input. | Manage that DPTI and Lead Agency specific timeframes are incorporated into the detailed program. | Develop the detailed project program including milestones, staging and DPTI timeframes utilising input from other team members as appropriate. | Provide input into the development of the project program.
| Identify approvals required for the project |  | R |  | R | R |  |  |  | I | I | Identify Government approvals and consult with DPTI re Development, WH&S and other approvals required. | Identify Government approvals and consult with DPTI re Development, WH&S and other approvals required. | Identify required approvals. | Assist to identify approvals.
| Development approval |  |  |  | R | R |  |  | I | R | I |  |  | Manage that development approval is achieved | Assist in achieving development approval.
DOCUMENTATION PHASE |  | 5.3
DESIGN SERVICES | Review Design phase outputs. |  | R | I | I | I | R | I | I | I | I | Manage that Design Contract Material is reviewed and agree approach to any aspects of changed brief or unresolved problems. | Assist in the review of the Design Contract Material and adjust services brief to professional service contractors as required. | Review work done to date and agree approach to any aspects of changed brief or unresolved problems. | Review work done to date and agree approach to any aspects of changed brief or unresolved problems.
| Prepare contract documentation |  | I | I | I | R | I | I | I | R | I | Input to the preparation of contract documentation as it is prepared to review that the signed off brief is implemented and that any issues are referred to the Lead Agency and End Users for input/endorsement as appropriate. | Provide the design team with relevant DPTI and Government standards and policies in regard to preparation of contract documentation. | Manage the preparation of contract documentation that incorporates the work of disciplines and is comprehensive, coordinated, unambiguous and in accordance with DPTI and Government policies and standards. | Coordinate with the Contractor in the preparation of contract documentation that is comprehensive, coordinated, unambiguous and in accordance with DPTI and Government policies and standards. | Review the contract documentation on an ongoing basis to manage that it is in compliance with the cost plan advising of any cost issues that arise.
| Define required quality standards for the contractor |  | I | I | I | R | I | I | I | R | I | Advise of the detailed requirements in regard to quality standards. | Manage that the design team is advised of the detailed brief requirements for quality standards. | Incorporate the briefed quality standards into the contract documentation. | Incorporate the briefed quality standards into the contract documentation. | Incorporate the briefed quality standards into the cost plan.
| Initiate and facilitate approvals related to the Development Act |  |  |  | I | R |  | I |  | R | I |  | Assist the Contractor to achieve Building Certification by providing liaison with DPTI certifier and Asset Services where appropriate. | Manage that the required Development Act Building Rules Assessment approvals are achieved to project program and that any aspects of concern are fully resolved within the design and cost plan. Modify design if required to comply with approval conditions and obtain signed certificate from Building Certifier confirming compliance. | Assist the design team to achieve Building Certification.
| Schedules |  |  |  | I | R |  |  | I | R | I |  |  | Provide all required schedules of materials, finishes, colours, fittings and fixtures. Review all schedules to manage that they are complete and clear. | Provide all required schedules. Review all schedules to manage that they are complete and clear. | Review all schedules to manage that they are included in the cost plan.
| Furniture, Fittings and Equipment |  | R |  | I | I | R | I | I | I |  | Establish a FF&E selection and budgeting process in liaison with the Lead Agency and End Users and agree the procurement process and timing with DPTI and the Project Manager. Liaise with the Contractor on selection of materials and colours for FF&E. |  | Establish with the Project Director a process of FF&E selection and procurement inclusive of the financial accounting of commitment and expenditure. Propose selections for soft furnishings and FF&E. Incorporate as required in the contract documentation. |  | Liaise with the Project Director on an ongoing basis to manage the reporting of FF&E cost and commitment in the monthly cost report.
| Endorsement of materials, finishes and colour selections |  | R | I | I | I | R | I | I | I | I | Manage that all appropriate presentations are made through the SC to the Lead Agency and End Users to endorse the materials and colour selections. |  | Assist the Project Director to achieve endorsement of the materials and colours. Manage that there is a process for achieving endorsement by the Lead Agency and End Users of the materials and colours. | Input as necessary to the selection of materials, finishes and colours. | Review materials, finishes and colour selections for any cost impacts.
| Prepare Preliminaries, General Requirements, Conditions of Tendering and Conditions of Contract |  |  |  | R | I |  | I |  | R | I |  | Determine the Conditions of Tendering and Conditions of Contract and provide design team with standard Preliminaries, General Requirements clauses and manage that the contract documentation meets the DPTI standards and requirements | Prepare contract documentation is accordance with DPTI determined Conditions of Tendering, Conditions of Contract, Preliminaries, General Requirements and other DPTI standards and requirements | Prepare contract documentation is accordance with DPTI determined Conditions of Tendering, Conditions of Contract, Preliminaries, General Requirements and other DPTI standards and requirements
| Comply with DPTI Guide Notes |  |  |  | I | R |  | I | R | R | I |  | Manage that the design team is advised of the relevant DPTI Guide Notes. | Comply with DPTI Guide Notes. Manage that all disciplines have copies of relevant Guide Notes. | Comply with DPTI Guide Notes.
| Design Review |  | I | I | R | I | I |  | I | I | I | Participate in DPTI design review when the drawings, specification and schedules are sufficiently complete to allow a full and detailed review of contract documentation | Manage and implement the DPTI design review when the drawings, specification and schedules are sufficiently complete to allow a full and detailed review of contract documentation with Lead Agency, End Users and design team. | Participate in DPTI design review when the drawings, specification and schedules are sufficiently complete to allow a full and detailed review of contract documentation. | Participate in DPTI design review when the drawings, specification and schedules are sufficiently complete to allow a full and detailed review of contract documentation.
| Budget Review |  | I | I | R | I | I | R | I | I | I |  | Manage and implement the DPTI design review at completion of Documentation | Participate in DPTI budget review. | Participate in DPTI budget review.
| Obtain pre-tender estimate and associated cash flows |  |  |  | I | R |  | I | R | I | I |  | Provide the design team with relevant DPTI and Government standards and policies in regard to pre-tender estimates and cash flow prediction | Manage that there is the preparation of a pre-tender estimate and associated cashflows. | Liaise with the Cost Manager and input as appropriate in the preparation of the estimate and cashflow. | Prepare check estimate and cash flow predictions based on completed contract documentation.
| Delay rates |  |  |  | R | I | [6 empty] | Determine the daily Delay Rate for Principal caused delay and include in contract documents. |  |  | Assist the DPTI Budget Risk Adviser to determine the Principal caused delay rate to be incorporated into tender documents.
| Contingencies |  |  |  | R | I |  | R | I | I | I |  | Contribute to the assessment of contingency allowances on the basis of risk analysis. | Determine the appropriate levels of contingency provision in consultation with the Lead Agency and DPTI. | Contribute to the DPTI assessment of contingency allowances on the basis of risk analysis. | Contribute to the DPTI assessment of contingency allowances on the basis of risk analysis.
| Utilise Contractor's register to select tenderers |  | I |  | R | I |  | R | I | I | I |  | Manage that there is an evaluation of the value of construction and determination of the required prequalification category for general building contractor and subcontractors and that these requirements are incorporated into tender documents. | Contribute to the selection of prequalification category for all contracts and subcontracts over $150,000 in value | Contribute to the selection of prequalification category for all contracts and subcontracts over $150,000 in value | Analyse the construction cost to determine any trade contracts and subcontracts over $150,000 in value and advise.
| DELIVERABLES | 5.3 | [6 empty] | R | R | R |  |  | One electronic and one hard copy of integrated and coordinated Contractor and disciplines' prepared Documentation phase Contract Material including specification, drawings, schedules, room data sheets and dilapidation report as applicable. Building Rules certification including certified drawings. | One electronic copy of Documentation phase Contract Material to Contractor to be incorporated into tender and contract documents. | One electronic and one hard copy of Documentation phase Contract Material.
TENDER |  | 5.4
APPROVAL | Approval to call tenders |  | R |  | I |  | R | I |  |  |  | Arrange for the Lead Agency delegate to approve the calling of construction tenders. | Manage that the Lead Agency approves the calling of construction tenders.
DESIGN SERVICES | Call tenders and obtain tender comparison estimate |  |  |  | R | I |  |  | I | I | I |  | Implement and manage the calling of construction contract tenders in compliance with procedures in AS4120-1994 Code of Tendering and the Code of Practice for the SA Construction Industry. Issue addenda as required. | Answer tender queries and prepare addenda as required for issue by DPTI. | Refer tender queries to the Contractor and coordinate with the Contractor in the preparation of addenda. | Prepare tender comparison estimate prior to close of tenders. Advise on the cost impact of any addenda issued.
| Evaluation processes |  |  |  | R | I | I | R | I | I | I | Participate in tender evaluation panels as required. | Manage the tender evaluation process strictly in accordance with DPTI policy, practices and systems. | Participate in the tender evaluation process in accordance with DPTI policy, practices and systems. | Participate in the tender evaluation process in accordance with DPTI policy, practices and systems.
| Alternatives |  |  |  | R | I | I | R | I | I | I | Participate in evaluation of tender alternatives as required. | Manage that the evaluation of alternatives is strictly in accordance with the DPTI alternatives evaluation policy. | Participate in the alternatives evaluation process in accordance with DPTI policy, practices and systems. | Participate in the alternatives evaluation process in accordance with DPTI policy, practices and systems.
| Prepare the tender appraisal and recommendation |  |  |  | R | I | I | R | I | I | I |  | Manage that there is a comprehensive contract compliance, price, alternatives and technical tender appraisal process completed with coordinated input from the design team and a tender recommendation prepared at its conclusion. | Contribute to the preparation of a comprehensive tender recommendation by DPTI. | Contribute to the preparation of a comprehensive tender recommendation by DPTI. | Prepare a reconciliation of tenders received, including assessment of alternatives, with the cost plan and pretender estimate.
| DELIVERABLES | 5.4 | [6 empty] | R | R |  |  |  | One copy technical tender appraisal incorporating disciplines appraisal. Schedule of post tender documentation and tender appraisal checklist. |  | One copy tender reconciliation
APPROVAL | Processing the tender call and final approval for awarding the construction contract. Up to $1 to <$11 million (Minister), <$1 Building Management |  | R |  | R |  | R |  |  |  |  | Manage that there is approval by the delegate of the expenditure to support the completion of the project. | Manage that there is approval by the delegate of contractor contracts required to complete the project.
Construction |  | 5.5
| Project Control Group |  | I | I | R | I | I | I | I | I | I | Attend and report to milestone Project Control Group meetings | Attend and report to milestone Project Control Group meetings | Chair, minute and report to regular Project Control Group meetings | Attend and report to regular Project Control Group meetings | Attend and report to regular Project Control Group meetings
| Site Team Meetings |  | I | I | I | R | I | I | I | I | I | Attend milestone design team meetings as required. | Attend milestone site team meetings as required. | Implement, chair and minute regular design meetings of the project team | Attend regular site team meetings. | Attend regular site team meetings.
| Monthly Reporting Regime |  |  |  | R |  | I | R | R | R | I |  |  | Prepare and submit on a monthly basis a report incorporating comments from disciplines providing status of all work and nominating all issues of concern and the management being applied to them. Consult with DPTI Project Risk Manager and Design Risk Adviser. | Input on a monthly basis to report prepared by the Contractor providing status of all work and nominating all issues of concern and the management being applied to them. | Prepare and submit on a monthly basis a report providing status of budget, commitment and analysis of trends in contingency expenditure nominating all issues of concern and the management being applied to them. Consult with DPTI Budget Risk Adviser.
CONTRACT ADMINSTRATION SERVICES | Award the construction contract |  | I |  | R |  |  | R |  |  |  |  | Manage that DPTI issues the acceptance and extension letters to contractors and professional service contractors.
| Manage the construction contract |  |  |  | R | I | I | R | I | I | I |  | Establish and implement all project management and administrative frameworks between all professional service contractors, DPTI and other relevant parties to manage effectively administration of the construction contract. | Participate in administration of the construction contract as delegated by the Superintendent and resolve coordinating with the subcontractors any technical issues raised by the construction contractor and/or the Lead Agency and End Users. | Participate in administration of the construction contract and resolve, coordinating with the Contractor any technical issues raised by the construction contractor and/or the Lead Agency and End Users. | Implement administrative processes for construction contract payment claims and variations in accordance with DPTI requirements.
| Attend site |  |  |  | I | R |  | I | I | R | I | Attend the construction site as required by the on-site activity. | Attend the construction site as required by the on-site activity. | Attend the construction site and inspect the works in accordance with the DPTI Guide Notes for Professional Service Contractors and as required by the on-site activity. Prepare a site visit report on status of construction and issues requiring attention. | Attend the construction site and inspect the works in accordance with the DPTI Guide Notes for Professional Service Contractors and as required by the on-site activity. Prepare a site visit report on status of construction and issues requiring attention. | Attend the construction site in accordance with the DPTI Guide Notes for Professional Services Contractors and as required by the preparation of payment claims.
| Queries |  |  | I | I | R | I | I | I | R | I | Promptly refer any general queries to the Project Manager and any contractual queries to the DPTI Project Risk Manager. | Establish a system for promptly responding to and processing all information or contractual questions. | Promptly answer Contractor's queries and issue explanatory information and details as required in accordance with contract procedure. | Promptly answer Contractor's queries and issue explanatory information and details through the Contractor and as required in accordance with contract procedure.
| Shop drawings |  |  |  | I | R |  |  |  | R | I |  |  | Establish a system for promptly processing all shop drawings. Coordinate all responses to the construction contractor to be within the time limits established under the construction contract. | Examine shop drawings for general compliance with construction contract.
| Off-site fabrication |  |  |  | I | R |  | I | I | R | I |  | Participate in administration of off-site fabrication and payment as delegated under the contract. | Review all construction contractor proposed arrangements for off-site fabrication for compliance with the construction contract. | Assist in the review all construction contractor proposed arrangements for off-site fabrication for compliance with the construction contract.
| Variations and claims management |  |  |  | R | I |  | R | I | R | I | Manage the approval of any required additional expenditure by the delegate. | Establish a system for promptly responding to all claims which ensures they are promptly assessed, endorsed and certified within the time limits under the construction contract. Make recommendation for additional expenditure as required and/or implement system of savings offsets. | Prepare and issue Variation Orders as required. Consider when preparing Variation Orders, whether there is any requirement to refer the modified design to the Certifier for review and certification. Participate in variations and claims management as delegated under the contract. | Prepare Variation Orders for forwarding by Contractor. Input as required in the assessment of any construction contract claims. | Assess and make recommendation on variation claims within the contract time limits. Monitor status of variations and provide monthly cost report detailing all professional service and construction contractor contract costs. Reconcile the progressive project costs with the budget and make recommendation for additional funding as required.
| Contract memos |  |  |  | R | I |  | R | I | I | I |  | Establish a system for the issue of Contract Memos under the construction contract. | Prepare Contract Memos as required for issue. | Prepare Contract Memos as required for issue.
| Payments |  |  |  | R | R |  | I |  | R | I |  | Establish a system for responding to all progress claims which ensures they are promptly assessed, endorsed and certified within the time limits under the construction and professional service contractor contracts. | Assist with the assessment of payment claims as required. | Assist with the assessment of payment claims as required. | Implement the DPTI payment system. Manage that all time limits for processing of claims are strictly adhered to. Prepare Recipient Created Tax Invoices/Tax Invoices for DPTI authorisation.
| Engineering service, access and temporary works interruptions |  | R | I | I | I | R | I | I | I | I | Liaise with the design team and pre-plan all service interruptions so as to minimise the impact upon End User operation. | Manage that the design team incorporate the Lead Agency requirements in regard to services interruptions into proposals. | Implement pre-planning of End User service interruption. Manage that all agreed prior notice periods are complied with by the construction contractor. | Participate in the pre-planning of End User service interruption.
| Procure Furniture, Fittings and Equipment |  | R | I | I | I | R | I | I | I | I | Procure FF&E in accordance with the agreed program. | Review with the Project Director the process of FF&E procurement and the reporting of commitment and expenditure. | Assist with the procurement of FF&E as required and administer items procured under the construction contract. |  | Liaise with the Project Director on an ongoing basis to manage the reporting of FF&E cost and commitment in the monthly cost report.
| Extension of time | [10 empty] | Manage the approval of any required additional expenditure by the delegate. | Establish a system for promptly responding to all claims for extension of time within the time limits under the construction contract. Make recommendation for additional expenditure as required and/or implement system of savings offsets. | Manage and issue extension of time claims as delegated under the construction contract.
| Commission and hand-over of the completed project |  | I | I | R | I | I | R | I | R | I | Manage that the End Users are prepared for occupation in accordance with the construction contract program. | Establish a process for effective management of commissioning and practical completion (or equivalent) under the construction contract. | Prepare defects list and make recommendation to DPTI on practical completion. Review and compile construction, operating and maintenance information required by the construction contractor for maintenance manuals and deliver to DPTI. | Prepare defects list and make recommendation to the Contractor re practical completion. Review and compile as-built drawings, construction, operating and maintenance information and deliver to the Contractor.
| DELIVERABLES | [5 empty] | R | R | R | R |  | Approval of additional expenditure if required | Recommendation for additional expenditure if required and contracts finalised | Record and report of site visits. Variation and extension of time recommendations. Practical Completion written recommendation. Defects Lists. | Variation Requests, Defects Lists, Operating and Maintenance Information | Progress Reports, Progress Payment Certificates Budget reconciliation recommendations
REVIEW PHASE |  | 5.6
CONTRACT ADMINSTRATION SERVICES | Defects Liability |  |  | I | R | I |  | R |  | I | I | Liaise with the Project Manager to advise of any defect issue which arises in the construction contract defects liability period (if applicable). | Establish a process of defect reporting and rectification. | Implement a process of defect reporting with the End Users and design team and for rectification with the construction contractor. Monitor requests for defects rectification during the construction contract defects liability period. Manage that the design team inspect the works at the end of the defects liability period and manage that the construction contractor completes the defects. | Liaise with the Contractor through the defects liability period to address any relevant defects issues. Undertake an inspection of the works at completion of the defects liability period and document all defect items.
| Contract finalisation. |  | R |  | R | I | R | R | I | I | I | Manage the approval of any required additional expenditure by the delegate. | Make recommendation that the contracts with the Contractor, Cost Manager, other disciplines and the contractor are finalised, final accounts paid and security released including recommendation on any additional expenditure required. | Assist DPTI as required to finalise accounts for all professional service contractors and contractors. Keep DPTI informed of all potential issues that might impact upon the finalisation of accounts. | Assist the Contractor as required to finalise accounts. | Prepare reconciliation of final accounts for professional service contractors and construction contractor with expenditure approvals and make recommendation on any additional expenditure requirement and settling of final accounts.
| Prepare Performance Reports |  |  |  | R |  | I | R | I | I | I | Prepare and submit DPTI Prequalification performance reports if requested by DPTI. | Manage the preparation of DPTI Prequalification performance reports on professional service contractors, disciplines, General Building Contractor, Subcontractors or Trade Contractors. | Prepare and submit DPTI Prequalification performance reports if requested by DPTI. | Prepare and submit DPTI Prequalification performance reports if requested by DPTI.
| Return Files |  |  |  | R |  |  |  | R | R | R |  |  | Return files to DPTI at completion of project in accordance with DPTI records management policy. | Return files to DPTI at completion of project in accordance with DPTI records management policy.
| DELIVERABLES | 5.6 |  |  |  |  | R | R | R | R | R | Final expenditure approval | Contracts finalised | As-built drawings where requested in the Contract. Prequalification Performance Report within 4 weeks of request to prepare. Report on the progressive rectification of defects. Final Certificate written recommendation. Files. | Files and as-built drawings where requested in the Contract | Reconciliation of final contract costs. Reconciliation of final project costs. Files.